## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2191-swen-261-01-b brapchads
11/11 notes | Jumping (single or multi) into the king row prohibits the game from continuing
If I challenge another player and immediately resign then the other player is not notified and is brought into a game against no one
If one [layer resigns and exits, when the other player refreshes the page they are still in the game
King Multijumps unsubmittable
If don’t make all possible jumps in a king multijump it lets you submit
King jumps arent forced in certain cases… weird af. (Might have something to do with Backup, but definitely need to check your move validation)
King when you submit instead of king when you attempt to move into the king row. King wont go back to a regular piece when you Backup
Consider a username character limit

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments | Cross Team | Tester initials; date; comments
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2019 | Pass | 2019-11-11
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2021 | Pass | 2019-11-11
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2022 | Pass | 2019-11-11
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2023 | Pass | 2019-11-11
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2024 | Pass | 2019-11-11
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2025 | Pass | 2019-11-11
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2019 | Pass | 2019-11-11
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2019 | Pass | 2019-11-11
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2021 | Pass | 2019-11-11
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2022 | Pass | 2019-11-11
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2023 | Pass | 2019-11-11
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2024 | Pass | 2019-11-11
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | CC, 11/4/2019 | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2025 | Pass | 2019-11-11
As a player I want to move a piece diagonally when no jumps are available so that the game can continue. | Given that it is my turn when I drag one of my pieces onto a board tile then I expect the game to check if my move is valid. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2019 | Pass | 2019-11-11
| Given my move is valid when I submit my move then I expect the piece to move to that tile permanently. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
| Given that I have submitted the move I have made when my opponent's screen refreshes then I expect their board to reflect my move. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2021 | Pass | 2019-11-11
| Given that it is my turn when I submit my move then I expect my opponent to be able to take their turn. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2022 | Pass | 2019-11-11
| Given that it is my opponent's turn when they submit their move then I expect to be able to take my turn. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2023 | Pass | 2019-11-11
| Given that I move one of my checker pieces diagonally and a jump cannot be made when I submit my move then I expect the move to be recognized as valid. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2024 | Pass | 2019-11-11
| Given that I move one of my checker pieces diagonally and a jump can be made when I submit my move then I expect an informative error message explaining why my move is invalid. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2025 | Pass | 2019-11-11
As a player I want to create a king piece when moving a piece to the top row so that I will have a king piece as defined by the American Rules for Checkers. | Given that a piece starts on one side of the board when it reaches the other side then it will be replaced with a king piece. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2019 | Pass | 2019-11-11
As a player I want to jump a piece and chain extra jumps if possible/necessary so that I can capture pieces as required by the American Rules for Checkers. | Given that there is an opponent diagonal to my piece and an empty spot past their piece when I submit a move that jumps over them then I expect my move to be valid. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2019 | Pass | 2019-11-11
| Given that I move a piece diagonally over an opponent's piece when there is no empty spot past the piece when I submit the move then I expect an invalid move error. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
| Given that there are a series of pieces diagonal to one of my pieces with an eventual open spot past the pieces when I submit a jump move that hops over all pieces then I expect the move to be invalid. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2021 | Pass | 2019-11-11
| Given that more than one jump move can be made when I submit any one of the jump moves then I expect the move to be valid. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2022 | Pass | 2019-11-11
| Given that I can make a jump move when I submit the jump move then I expect the piece that I jumped over to be removed from the game board. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2023 | Pass | 2019-11-11
| Given that a jump type move can be made when I submit a standard type move then I expect to receive an invalid move error message. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2024 | Pass | 2019-11-11
| Given that more than one jump moves can be chained together when I attempt to submit my move before chaining all jumps together then I expect the move to be invalid. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2025 | Pass | 2019-11-11
| Given that multiple jumps move can be chained together when I submit my move that chains all jumps together then I expect the move to be valid. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2026 | Pass | 2019-11-11
| Given that I chain multiple jump moves together and the move is valid when I submit the move then I expect all pieces that I jumped over to be removed. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2027 | Pass | 2019-11-11
| Given that I jump over one or more of my own pieces when I submit my move then I expect my move to be invalid. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2028 | Pass | 2019-11-11
As a player I want to know when a game is over so that I can return to the player lobby and find a new match. | Given it is my turn to move in a game of checkers when all my pieces are blocked by my opponent then I will lose the game. |  |  |  |  | Pass | CSC; 11/25/2019 | Pass | 2019-11-11
| Given that it is my turn when I capture the last of my opponents pieces then I expect to win the game. |  |  |  |  | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
| Given that it is my turn when I push then resign button then I expect to lose the game. |  |  |  |  | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
As a developer I want to restrict the player to moves legal under the American Rules for Checkers so that they cannot perform illegal moves. | Given that a piece is not a king when I submit a move in the backwards diagonal direction then I expect my move to be invalid. |  |  |  |  | Pass | CSC; 11/25/2019 | Pass | 2019-11-11
| Given that a spot diagonal to my piece is occupied when I attempt to move my piece into that spot then I expect the move to be invalid. |  |  |  |  | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
| Given that I move a piece onto a white space when I submit the move then I expect the move to be invalid. |  |  |  |  | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
| Given that a jump move can be made when I submit a move that is not a jump move then the move will be invalid. |  |  |  |  | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
| Given that multiple jump moves can be made when I submit a move that doesn't complete the jump chain then the move will be invalid. |  |  |  |  | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
| Given that my piece is on the left or right side of the checkerboard when I attempt to move a piece further to the left or right, respectively then I expect the move to be invalid. |  |  |  |  | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
| Given that my piece reaches the other side of the checkerboard when I attempt to move the piece forward then I expect the move to be invalid. |  |  |  |  | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
As a player I want to alternate taking turns between my opponent and myself so that I can have time to decide on the move I wish to make. | Given I just submitted a move when I attempt to make a move before my opponent has made a move then I expect the game to disregard my attempt. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2019 | Pass | 2019-11-11
| Given that my opponent just submitted a move when my opponent attempts to make a move before I have moved my piece then I expect the state of the board to remain unchanged. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
| Given that my opponent has made a move when I view my board then I expect to see the move that they made. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
As a player I want to be able to move a king piece backwards or forwards diagonally so that I utilize the piece as defined by the American Rules for Checkers. | Given that a jump move is possible with a king piece when the jump move is not submitted then it will be recognized as an invalid move. |  |  |  |  | Pass | CSC; 11/25/2019 | Pass | 2019-11-11
As a player I want to have the choice of jumping opponent pieces with a king piece in all four diagonal directions and chain extra jumps if possible/necessary so that I can remove as many of my opponents pieces from the board as possible. | Given that a single opponent's piece is diagonal to my king piece and there is an open spot behind it when a jump move is made then I expect the move to be valid. |  |  |  |  | Pass | CSC; 11/25/2019 | Pass | 2019-11-11
As a player I want to resign from a match so that I can acknowledge my loss and start a new match as soon as possible. | Given that I wish to end a match with an opponent when I attempt to resign then I expect my opponent to win while I receive a loss for the match. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2019 | Pass | 2019-11-11
| Given that I wish to end a match with an opponent when I resign from the match then I will be taken back to the player lobby. |  |  | Pass | CC, 11/4/2019 | Pass | CSC; 11/25/2020 | Pass | 2019-11-11
As a player I want to be able to move a king piece backwards or forwards diagonally so that I utilize the piece as defined by the American Rules for Checkers. | Given that a jump move is possible with a king piece when the jump move is not submitted then it will be recognized as an invalid move. |  |  |  |  | Pass | CSC; 11/25/2019
| Given that a piece is a king piece when I attempt to make a backwards move then the game accepts it as valid. |  |  |  |  | Pass | CSC; 11/25/2019
As a player I want to have access to a spectator option so that I can watch and learn how to play checkers. | Given that I wish to view a match between two players when I click on the names of the players that are in a match then I will be taken to the game between the two opponents in spectator mode. |  |  |  |  | Pass | CSC; 11/25/2019
As a player I want to know when a game is over so that I can return to the player lobby and find a new match. | Given it is my turn to move in a game of checkers when all my pieces are blocked by my opponent then I will lose the game. |  |  |  |  | Fail | CSC; 11/25/2019; No automatic failure, have to manually resign
| Given that it is my turn when I capture the last of my opponents pieces then I expect to win the game. |  |  |  |  | Pass | CSC; 11/25/2019
| Given that it is my turn and I haven't made a move or it is not my turn when I push then resign button then I expect to lose the game. |  |  |  |  | Pass | CSC; 11/25/2019; BUG: Game exits for resignee, but appears as still running to opponent when done on first turn
As a player I want to have the choice of jumping opponent pieces with a king piece in all four diagonal directions and chain extra jumps if possible/necessary so that I can remove as many of my opponents pieces from the board as possible. | Given that a single opponent's piece is diagonal to my king piece and there is an open spot behind it when a jump move is made then I expect the move to be valid. |  |  |  |  | Pass | CSC; 11/25/2019
| Given that there is multiple jumps may be chained together by hopping over successive opponent's pieces in any diagonal direction then when I submit my turn then it will be valid. |  |  |  |  | Pass | CSC; 11/25/2019
| Given that I may perform a jump in any direction when I submit my turn without making a jump then my move will not be valid. |  |  |  |  | Pass | CSC; 11/25/2019
As a developer I want to restrict the player to moves legal under the American Rules for Checkers so that they cannot perform illegal moves. | Given that a piece is not a king when I submit a move in the backwards diagonal direction then I expect my move to be invalid. |  |  |  |  | Pass | CSC; 11/25/2019
| Given that a spot diagonal to my piece is occupied when I attempt to move my piece into that spot then I expect the move to be invalid. |  |  |  |  | Pass | CSC; 11/25/2019; NOTE: Move cannot be made at all
| Given that I move a piece onto a white space when I submit the move then I expect the move to be invalid. |  |  |  |  | Pass | CSC; 11/25/2019; NOTE: Move cannot be made at all
| Given that a jump move can be made when I submit a move that is not a jump move then the move will be invalid. |  |  |  |  | Pass | CSC; 11/25/2019; NOTE: Only marked invalid when trying to submit
| Given that multiple jump moves can be made when I submit a move that doesn't complete the jump chain then the move will be invalid. |  |  |  |  | Pass | CSC; 11/25/2019
| Given that my piece is on the left or right side of the checkerboard when I attempt to move a piece further to the left or right, respectively then I expect the move to be invalid. |  |  |  |  | Pass | CSC; 11/25/2019; NOTE: Move cannot be made at all
| Given that my piece reaches the other side of the checkerboard when I attempt to move the piece forward then I expect the move to be invalid. |  |  |  |  | Pass | CSC; 11/25/2019; NOTE: Move cannot be made at all
| Given that my piece is not diagonally adjacent to a spot when I attempt to move my piece to it then I expect the move to be invalid. |  |  |  |  | Pass | CSC; 11/25/2019; NOTE: Invalid move message is snarky, should be changed
As a developer I want to design a Spectator class so that I can provide an outlet to those who want to watch people play checkers. | Given that I want to learn how to play checkers when I enter spectator mode then I am able to view two players competing in a game of checkers. |  |  |  |  | Pass | CSC; 11/25/2019
| Given that I am playing a game of checkers with an opponent when a spectator enters the game then I expect that the spectator has no ability to modify any of the pieces on the board. |  |  |  |  | Pass | CSC; 11/25/2019
| Given that I am spectating a game of checkers when the game is over then I expect to be able to review the game using the replay module. |  |  |  |  | Fail | CSC; 11/25/2019; Replay not implemented in master
| Given that a spectator is viewing a match when they leave the match then the game continues as expected for the two competitors. |  |  |  |  | Pass | CSC; 11/25/2019
As a player, I want to be able to leave the match and return at a later time so that I can perform another task while in a match. | Given that I go to the home page mid-game, when I rejoin the game then I expect the game state to remain unchanged. |  |  |  |  | Pass | CSC; 11/25/2019; NOTE: Game state can be changed by other player (as expected)
| Given that I sign out mid-game, when I sign back in then the game will still be available to continue |  |  |  |  | Pass | CSC; 11/25/2019
| Given that it is my turn when I leave a game, when I return then it will still be my turn. |  |  |  |  | Pass | CSC; 11/25/2019
| Given that it is not my turn, when I leave a game then I expect my opponent to be able to make a move when I'm not there. |  |  |  |  | Pass | CSC; 11/25/2019
As a player I want to have the option to enter replay mode so that I can rewatch a previous game of checkers. | Given that I wish to rewatch a match between two players when I click on the names of the players that competed in the match then I will be taken to the replay module to rewatch the match in replay mode. |  |  |  |  | Fail | CSC; 11/25/2019; Replay not implemented in master
| Given that I wish to leave the replay module when I press the exit button then I expect to be taken back to the home page and placed in the player lobby |  |  |  |  | Fail | CSC; 11/25/2019; Replay not implemented in master
As a player I want to have the option to step forward or backwards a move in the replay module so that I can analyze a game of checkers at the speed I prefer. | Given that I am in the replay mode when I click on the next button then I expect the board to update according to the next move. |  |  |  |  | Fail | CSC; 11/25/2019; Replay not implemented in master
| Given that I am in the replay mode when I click on the previous button then I expect the board to update according to the previous move. |  |  |  |  | Fail | CSC; 11/25/2019; Replay not implemented in master
As a player I want the choice to save a replay when setting up a game so that I will have a replay file if desired. | Given that I am competing in a match when the game is over then I expect to have to option to review the match via the replay module. |  |  |  |  | Fail | CSC; 11/25/2019; Replay not implemented in master
| Given that I am using the replay module when I attempt to understand the mechanics of the match then I expect to be able to step forward and backward through the match at my will. |  |  |  |  | Fail | CSC; 11/25/2019; Replay not implemented in master
| Given that I am at the home page when I want to view a previous replay then I expect to see a button that will show me previous matches that have been played such that I can select one to replay. |  |  |  |  | Fail | CSC; 11/25/2019; Replay not implemented in master
| Given that I am finished with the replay module when I push the button in the module to return to the lobby then I expect to be signed-in and placed back in the player lobby. |  |  |  |  | Fail | CSC; 11/25/2019; Replay not implemented in master
| Given that I want to view a recent replay of mine when I enter the replay module then I expect to be removed from the player lobby. |  |  |  |  | Fail | CSC; 11/25/2019; Replay not implemented in master
| Given that I have recently entered the replay module when a player tries to compete against me in checkers then they should receive an appropriate error message. |  |  |  |  | Fail | CSC; 11/25/2019; Replay not implemented in master
| Given that a game was already played by two other players when I click on the replay button for that particular game then I should be able to replay that game. |  |  |  |  | Fail | CSC; 11/25/2019; Replay not implemented in master